## Sheet1
This checklist will assist you in transferring a client from a fully-insured to self-funding arrangement. Download this tool and customize to your firm for a seamless process for your client and team.
Organization:
START DATE:
Self-Funding Analysis | Start Date - | Notes
Market Analysis
Actuarial Analysis (self-funded feasibility)
TPA Selection
Stop Loss Carrier RFP
Pharmacy Benefit Manager RFP
Disease Management
Large Case Management
Care Coordination Vendor
Nurse Navigator Service
Accounting Overview
Captive Analysis (if necessary) | Start Date - | Notes
Captive Manager
Domicile
Group Captive review (which program)
Funding the captive
Legal documents
Interview current members
Stop Loss Carrier | Start Date - | Notes
Disclosure statement to client for signature
Signed disclosure statement to Stop Loss Carrier
Request current claims data
Request incumbent renewal
Send claims data and incumbent renewal to Stop Loss Carrier
Stop Loss Carrier issues application - send to client
Send signed application to Stop Loss Carrier
Stop Loss Carrier prepares binder check statement - verify amounts and numbers
Client remits binder check to Stop Loss Carrier
Send copy of binder check to TPA and request they credit first month's invoice
Confirm application, disclosure and binder premium received by carrier
Confirm stop loss coverage is bound in writing
Stop loss policy issued and reviewed
Stop loss policy shared with TPA and client
TPA | Start Date - | Notes
Schedule new client/implementation call with TPA
New client forms reviewed, completed, and submitted to TPA
Current plan documents received and sent to TPA (discuss any plan design changes)
Schedule TPA service team introduction call
Complete and submit client banking set-up
TPA create SPD and InCite review Draft
Final draft of plan document approved by InCite, TPA, and PBM
Drafted plan document to client for review and approval
Signed plan document to stop loss carrier for acceptance
Ensure TPA feeds are set-up for PBM, Patient Care, and BI
Review and Approve ID Cards (verify that PBM has ok'ed card)
Provide billing rates to TPA - SL premiums, admin fees, broker fees, PBM fees, etc.
Request copy of draft initial bill from TPA (prior to billing client)
Confirm TPA is live and paying claims
Pharmacy Benefit Manager | Start Date - | Notes
Request current PBM set up documents - send setup documents to PBM
Schedule implementation/plan build call with client and PBM team
Review and approve PBM's benefit builder
Send approved benefit builder to TPA
Current PBM - request open PA's and list of specialty med users
Current PBM - request claim file to identify disruption under new PBM
Current PBM - identify specialty medication users
Share current PBM reports (open PA's, claim file, specialty meds) to new PBM
Discuss PA, speciality meds, and disruption report with client to identify EE communication needs
Verify that group billing/claims processing is correctly set-up with TPA
Care Coordination | Start Date - | Notes
Complete Implementation Guide - send to Care Coordinator
Send all current and former plan documents (up to 2 years old) to Care Coordinator
Schedule implementation/introduction call with Care Coordinator and client
Client complete Care Coordinator BAA
Client complete TPA PHI release for Care Coordinator advocates to access claim system
Review employee communication plan and materials
Share client logo with Care Coordinator for reporting/branding of materials
Health Risk Management | Start Date - | Notes
Review HRM approach
Incentive structure
Develop HRM plan
Develop EE communication plan for HRM
Self-Funding Transition Checklist